## Master
No. | Action Required | Status (On track, Off track, Closed) | Priority (Must, Could, Should) | Area | System | Level of Effort | Notes | Lead | Date Initiated | Delivery Date | Change Impact | Action Taken | Comments

## Data
Systems
EasyEmployer
Skedulo
Skedulo App
Aurion
CRM
TCM
CRM/Tech1
CRM/Skedulo
Rostering/EE
Tech1
L&D
MCW
Legacy
Change Mgt
Business Process
Area
SCHADS
Payroll
Pay Cycle
Rostering
Client Services
Training
General
Change Mgt
M/S/C
Must
Could
Should
Decision
Status
Not Started
Started - On Track
Started - Off Track
Completed
Paused
Post Project
Decision Pending
Removed
Level of effort
Small
Medium
Large
Unknow

## SCHADS (hidden)
Action & Follow Up Log
Area: | SCHADS
No. | Action Required | Area | Priority (Must,Could,Should) | Date Initiated | Delivery Date | ADKAR Rating (A-Aware, D-Desire, K-Knowledge, A-Ability, R-Reinforce) | Action Taken | Status (On track, Off track, Closed) | Comments
1 | Consultation – with Staff | SCHADS | Must | [5 empty] | This is just one of many things that are associated with item 8 - recommend removing this, or putting it at the bottom of this list
2 | Lessons learnt from CPL SCHADS - testing | SCHADS | Must | [5 empty] | Recommend this is done very sonn & documented
3 | CTH pays the higher rate when billing for the higher rate for evening - this needs to be reviewed to confirm whether or not this will continue to happen under SCHADS & if changing - must form part of consultation | SCHADS | Must | [5 empty] | For noting only and including in comms
4 | Comparison of Cootharinga EA v SCHADS to identify areas of difference | SCHADS | Must
5 | Costing of SCHADS v EA for Cootharinga |  | Must
6 | Develop full plan including timings for all activities based on CPLs process and including lessons learnt |  | Must
7 | SCHADs compliant roster to be done prior to implementation - including costing to ensure within funding envelope |  | Must
8 | CTH SCHADS training and education same as CPL |  | Must

## Centralised Payroll & Pay Cycle (hidden)
Action & Follow Up Log
Area: | Centralised Payroll
No. | Action Required | Area | Priority (Must,Could,Should) | Date Initiated | Delivery Date | ADKAR Rating (A-Aware, D-Desire, K-Knowledge, A-Ability, R-Reinforce) | Action Taken | Status (On track, Off track, Closed) | Comment
1 | Aurion to be used for payroll for the group | Centralised Payroll | Must
2 | Exit Smart Salary contract | Centralised Payroll | Must | [5 empty] | Have extended contract to 31 January 2024
3 | Self-service of pay slips for CTH | Centralised Payroll | [6 empty] | What does this mean?
4 | Leave requests to move to Aurion for non DSWs Cootharinga non-DSWs to be given access to Aurion | Centralised Payroll | Must
5 | DSW apply for leave by manual form similar to CPL | Centralised Payroll | [6 empty] | This feels like a statement rather than an action?
6 | Align payroll codes across the group | Centralised Payroll | Must | [5 empty] | This is required to ensure Rostering can work across the group using Skedulo
7 | Salary packaging – CTH is Access Pay, CPL Remserv opportunity to consolidate?? | Centralised Payroll
8 | Need to be able to access seven years of payroll data – Smart Salary first payment was in Jan 2019. The rest is in old TechOne. | Centralised Payroll | Must | [5 empty] | Is this just a note? This is the case no matter what we do re centralising payroll. Not sure why it’s on this list?
9 | Comms and training for Aurion | Centralised Payroll | Must
10
Area: | Pay Cycle
No. | Action Required | Area | Priority (Must,Could,Should) | Date Initiated | Delivery Date | ADKAR Rating (A-Aware, D-Desire, K-Knowledge, A-Ability, R-Reinforce) | Action Taken | Status (On track, Off track, Closed) | Comment
11 | Need to agree the pay cycle for the group | Pay Cycle | Must
12 | Need to land on the transition approach & timing | Pay Cycle | Must
13 | Comms |  | Must
14
15

## In2One (hidden)
Action & Follow Up Log
Area: | In2One
No. | Action Required | Area | Priority (Must,Could,Should) | Date Initiated | Delivery Date | ADKAR Rating (A-Aware, D-Desire, K-Knowledge, A-Ability, R-Reinforce) | Action Taken | Status (On track, Off track, Closed) | Comments
1 | Lessons learnt from Renaissance | In2One | Must | [5 empty] | Has this been done & documented?
2 | Map out plan & timing for moving Cootharinga TCM info into Lumary |  | Must
3 | TCM into Lumary | In2One | Must
4 | Setting up CTH DSW's in Skedulo and Easy Employer, including all required tags | In2One | Must
5 | Skills/Qualifications tags | In2One | [6 empty] | Is this part of item 4?
6 | Clients preference for staff or blocked | In2One | [6 empty] | Is this part of item 4?
7 | Remote and very remote pricing to be set up in Lumary as CPL do not currently use them | In2One | Must
8 | Update all aged care rates / home care packages and other non-NDIS rates for Cootharinga & ensure correct in Lumary | In2One | Must
9 | DEX reporting for CTH and aged care currently runs a report from TCM – new process and comms needed | In2One | Must
10 | CTH invoice from Lumary? | In2One | [6 empty] | Cootharinga's invoices are directly from TechOne using ETL of data from TCM to TechOne. Ideally CPL will move to this methodology before In2One is ready to go live too
11 | Equipment solutions - what | In2One |  |  |  |  | TBA if in scope |  | What does this mean?
12 | MCW = Skedulo Mobile App | In2One | [6 empty] | Is there an action around this? Wouldn't they move to the Skedulo app?
13 | Client notes - CTH capture in mobile app | In2One | [6 empty] | Can we increase functionality of Skedulo app (or a new app) to ensure Cootharinga don't go backwards & ideally CPL would capture notes on app too
14 | Decision needed re length of data to be set up - Forward and backward roster depth of data to put in. | In2One | Must
15 | Set up new rosters for CTH from scratch in Skedulo | In2One | Must
16 | UAT for setup of this and test and who can access | In2One | [6 empty] | What is "this"? Rosters? DSWs? Something else?
17 | Quality process before making them SCHADS compliant make sure they are funded correctly. | In2One | [6 empty] | This is covered by a SCHADS action - recommend removing
18 | Archiving TCM | In2One | Should
19 | Process to be developed / agreed for clients that are a client of both CPL and Cootharinga - how will this be managed | In2One | Must
20 | Decision to be made: What do we mean for centralised rostering? Is this a team or just technology? | In2One | Must
21 | After hours and access to CTH records in Lumary and Skedulo. Cootharinga don't really have After Hours Team currently. This will move into the group after hours service. | In2One | [6 empty] | Does the After Hours Team now manage both orgs? They didn’t initially but I thought they did now?
22 | How will / can we handle DSWs that work across both CPL and Cootharinga? |  | Must
23 | Skedulo App - Timesheet Approval | [7 empty] | Unsure what this means in this context?

## Other (hidden)
Action & Follow Up Log
Area: | Other
No. | Action Required | Area | Priority (Must,Could,Should) | Date Initiated | Delivery Date | ADKAR Rating (A-Aware, D-Desire, K-Knowledge, A-Ability, R-Reinforce) | Action Taken | Status (On track, Off track, Closed) | Comments
1 | Opportunity for Enable HR to be used for the Group |  | Could | [5 empty] | What do CPL currently use? Anything? Or just network (and no system)?
2 | Decision: Use of Job Adder or MR+ & Seek for recruitment across the group |  | Could
3 | Data flow into Aurion and or Enable HR | [7 empty] | Is there an action for this? Unclear what it means?
4 | LITMOS already being used by Cootharinga | Litmos | [6 empty] | Ok…. Is there an action needed? Or is it just a comment to be captured? Can we delete / mark as complete?
5 | Some training records kept here some in Enable HR - to be consolidated | Litmos | [6 empty] | "Here" being Litmos?
6 | Checking the codes for training | Litmos | [6 empty] | What does this mean?
7 | Storing and archiving of records | Litmos | [6 empty] | What does this mean?
8 | New Org for CTH | EasyEmployer | [6 empty] | There will be a lot more to it than this - recommend a full list of EE requirements for Cootharinga
9 | New CTH staff | EasyEmployer | [6 empty] | As above
10 | Public Holidays are slightly different | EasyEmployer | [6 empty] | What does this mean?
11
12
13
14
15

## NOT UPDATED Consolidated List (hidden)
Action & Follow Register
Area: | Consolidated
No. | Action Required | Area | Priority (Must,Could,Should) | Level of effort | Change management required | Order | Notes | Lead | Date Initiated | Delivery Date | ADKAR Rating (A-Aware, D-Desire, K-Knowledge, A-Ability, R-Reinforce) | Action Taken | Status (On track, Off track, Closed)
1 | Opportunity for Enable HR to be used for the Group | Enable HR | Could |  |  |  | Investigate at another time.
2 | Decision: Use of Job Adder or MR+ & Seek for recruitment across the group | Enable HR | Could |  |  |  | Investigate at another time.
3 | Data flow into Aurion and or Enable HR | Enable HR | Must | Large |  |  |  | Melissa R, Rachel N
4 | LITMOS already being used by Cootharinga | Litmos |  |  |  |  | For noting only.
5 | Some training records kept here some in Enable HR - to be consolidated | Litmos | Must | Medium | Y |  | Investigate
6 | Checking the codes for training | Litmos | Must | Small |  |  | MB - Codes are the same. Updating codes not a big job if they are different. | Matt B
7 | Storing and archiving of records | Litmos |  |  |  |  | MattB - working on this | Matt B
8 | New Org for CTH | EasyEmployer | Must | Medium |  |  |  | Michael B
9 | New CTH staff | EasyEmployer | Must | Medium |  |  | Requires an operational process to add and remove CTH DSW based on Enable HR records. Could start with a manual process i.e. csv extract and upload. | Michael B, Melissa R
10 | Public Holidays are slightly different | EasyEmployer | Must | Medium |  |  |  | Michael B
11 | Consultation – with Staff | SCHADS | Must | Large |  | 1 | Need an idea of the timeframes for this. What is the rough length of time required for engagement. This item is a major dependency for the project. ^ - * weeks ? need Murray to confirm. | Murray ?
12 | Lessons learnt from CPL SCHADS - testing | SCHADS | Must | Small | Y? | 1 | To organise | Murray ?
13 | CTH pays the higher rate when billing for the higher rate for evening - this needs to be reviewed to confirm whether or not this will continue to happen under SCHADS & if changing - must form part of consultation | SCHADS | Must | Medium |  | 1 | CPL does not do this so a global decision needs to be made on this. Going to the PPP for a recommendation to ELT. | Angela H
14 | #ERROR! | SCHADS | Must | Very Large | Y | 2 | This is likely to require resources in order to do this. Sam to get a copy of the roster. KA to discuss with Alexis
15 | #ERROR! | SCHADS | Must | Medium | Y
16 | Comparison of Cootharinga EA v SCHADS to identify areas of difference | SCHADS | Must |  |  |  | Underway due end April. Seems straight forward
17 | Aurion to be used for payroll for the group | Centralised Payroll | Must | Large
18 | Exit Smart Salary contract | Centralised Payroll | Must | Small
19 | Self-service of pay slips for CTH | Centralised Payroll | Could |  | y
20 | Leave requests to move to Aurion for non DSWs Cootharinga non-DSWs to be given access to Aurion | Centralised Payroll | Must | Small | Y |  | Potentially lots of business process changes in this.
21 | DSW apply for leave by manual form similar to CPL | Centralised Payroll |  |  | y? |  | Can this be removed
22 | Align payroll codes across the group | Centralised Payroll | Must | ? |  |  | Needs investigation. If SCHADS then this may be easier than. Depends on what is grandfather
23 | Salary packaging – CTH is Access Pay, CPL Remserv opportunity to consolidate?? | Centralised Payroll | Could
24 | Need to be able to access seven years of payroll data – Smart Salary first payment was in Jan 2019. The rest is in old TechOne. | Centralised Payroll | Must | ? |  |  | Needs investigation
25 | Comms and training for Aurion | Centralised Payroll | Must | Small /medium | Y
26 | Communications | Pay Cycle | Must | Medium | Y
27 | Need to land on the transition approach | Pay Cycle | Must | Large | Y?
28 | Lessons learnt from Renaissance | In2One | Must | Medium | [7 empty] | Workshops carried out for this Closure report being developed.
29 | TCM into Lumary | In2One | Must | Large | Y? |  | Most of the CTH client in Lumary already. Some uplift maybe required. May need more files against the records. Client profiles or funding.
31 | Setting up CTH DSW's in Skedulo and Easy Employer, including all required tags | In2One | Must | Large |  |  | Data mapping and system integrations
32 | Skills/Qualifications tags | In2One | Must | Small/medium | Y? |  | We would try and use what is being done in this space for CPL tags and skills as both orgs use LITMOS
33 | Clients preference for staff or blocked | In2One | Must | Medium | Y?
34 | Remote and very remote pricing to be set up in Lumary as CPL do not currently use them | In2One | Must | Small |  |  | Done - part of testing
35 | Update all aged care rates / home care packages and other non-NDIS rates for Cootharinga & ensure correct in Lumary | In2One | Must | Small |  |  | They are aligned other than remote and very remote to double check
36 | DEX reporting for CTH and aged care currently runs a report from TCM – new process and comms needed | In2One | Must | Small | Y |  | Verify whether CPL are already doing this or if it is currently done out of CTH
37 | CTH invoice from Lumary? | In2One | Must |  |  |  | This may be another solution.
38 | Equipment solutions - what | In2One |  |  |  |  | Investigate - Wendy and James to discuss.
39 | MCW = Skedulo Mobile App | In2One | Must | small | Y |  | CPLG to capture notes in a consistent format and detail. Need to add TEA. Skedulo training ?
40 | Client notes - CTH capture in mobile app | In2One | Must | Large | Y |  | Needs investigation. Need to consider this for CPL maybe.
41 | Decision needed re length of data to be set up - Forward and backward roster depth of data to put in. | In2One | Must |  | Y? |  | Needs a decision to know what length of backwards roster. This relates to the ease of accessing TCM data.
42 | Set up new rosters for CTH from scratch in Skedulo | In2One | Must | Large
43 | UAT for setup of this and test and who can access | In2One | Must | Small | Y? |  | Education of access to UAT - training (could be tech advise )
44 | Quality process before making them SCHADS compliant make sure they are funded correctly. | In2One | Must | Medium
45 | Archiving TCM | In2One | Must | Medium |  |  | For access for a while
46 | Process to be developed / agreed for clients that are a client of both CPL and Cootharinga - how will this be managed | In2One | Must | Small | Y? |  | Needs investigation
47 | Decision to be made: What do we mean for centralised rostering? Is this a team or just technology? | In2One | Must | ? | Y? |  | Needs to be understood sooner or latter. Being discussed at ROTE. Layered with who is doing the rostering. Moved to ROTE for decision - SCB
48 | After hours and access to CTH records in Lumary and Skedulo. Cootharinga don't really have After Hours Team currently. This will move into the group after hours service. | In2One | Could |  |  |  | And is in progress. This could be done before this project.
49 | How will / can we handle DSWs that work across both CPL and Cootharinga? | In2One | Must | ? |  |  | Needs to be explored.
49 | Skedulo App - Timesheet Approval | In2One | Must | ? |  |  | Needs to be explored.